## විහාරස්ථාක1
Improvement of underdeveloped Dhamma schools- 2021
Progress on 2021.12.31
DS DIVISION - Thumpane
SN | Name and address of the Sunday school | The Ministry wich Allocated the Provisions | Project Proposal | Approved Allocation Amount Rs. | Implemented by | Estimated Amount | වියදම රු | Physical Progress | Financial Progress
1 | Sri Wimala Dhamma Dhamma School, Sri Gangaramaya, Opalla, Galagedara | Ministry of Buddhasasana, Religious and Cultural Affairs | Construction of toilet system for Dhamma school | 250000 | Divisional Secretariat | 250000 |  | 100% | 250000
2 | Sri Dharmarama Dhamma School, Keerthi Sri Rajasingharamaya, Kopiwatta, Kumburegama | Ministry of Buddhasasana, Religious and Cultural Affairs | Development of Dhamma School Building | 250000 | Divisional Secretariat | 250000 |  | 100% | 246749.42
3 | Sri Moggallana Dhamma School, Hitgoda Walpola Viharaya. Wettewa, Galagedara | Ministry of Buddhasasana, Religious and Cultural Affairs | Construction of new Dhamma School building. | 250000 | Divisional Secretariat | 250000 |  | 100% | 250000
|  | බුද්ධශාසන,ආගමික හා සංස්කෘතික කටයුතු අමාත්‍යාංශය | නව දහම් පාසල් ගොඩනැඟිල්ලේ ඉදි කිරීම්. | 250001 | Divisional Secretariat | 250001 |  | 100% | 250000
4 | Sri Dhammaloka Dhamma School, Daluggala Rajamaha Viharaya, Idamegama, Werellagama | Ministry of Buddhasasana, Religious and Cultural Affairs | Construction of toilet system for Dhamma school | 250000 | Divisional Secretariat | 250000 |  | 100% | 250000
[6 empty] | 1000000 |  |  | 996749.42
Underdeveloped Temples Improvement Program 2021
Progress on 2021.12.31
SN | Name and address of the Temple | The Ministry wich Allocated the Provisions | Project Proposal | Approved Allocation Amount Rs. | Implemented by | Estimated Amount | වියදම රු | Physical Progress | Financial Progress
1 | Sri Bodhirajaramaya Sri Siddharthodaya Pirivena Viharaya, Medagoda, Galagedara | Ministry of Buddhasasana, Religious and Cultural Affairs | Roofing the the Bhikku Education Hall | 500000 | Divisional Secretariat | 505552.47 |  | 100% | 500000
Pirivena Development Program -2021
Department of Cultural Affairs - Central Province
Progress on 2021.12.31
SN | Name and address of the Pirivena | The Ministry wich Allocated the Provisions | Project Proposal | Approved Allocation Amount Rs. | Implemented by | Estimated Amount | වියදම රු | Physical Progress | Financial Progress
1 | Niyangoda Kumburegama Sri Dharmaloka Maha Pirivana, Kumburegama. | Department of Cultural Affairs - Central Province | Development of toilet facilities at Niyangoda Kumburegama Sri Dharmaloka Maha Pirivena | 100000 | Divisional Secretariat | 100926.32 |  | 100% | 100000
Renovation of buildings of Pirivena educational institutions -2021
State Ministry of Dhamma School Pirivenas and Bhikku Education
Progress on 2021.12.31
SN | Name and address of the Pirivena | The Ministry wich Allocated the Provisions | Project Proposal | Approved Allocation Amount Rs. | Implemented by | Estimated Amount | වියදම රු | Physical Progress | Financial Progress
1 | Sri Dharmaloka Maha Pirivana Niyangoda | State Ministry of Dhamma School Pirivenas and Bhikku Education | Renovation of Buildings of Sri Dharmaloka Maha Pirivena Niyangoda, Pirivena Educational Institutions | 1000000 | Divisional Secretariat | 1036200 |  | 100% | 0
Water Sources and Water Resources Conservation Program -2021
Progress on 2021.12.31
SN | Project Proposal | The Ministry wich Allocated the Provisions | GN Division | Approved Allocation Amount Rs | Implemented by | Estimated Amount | වියදම රු | Physical Progress | Financial Progress
1 | Development of Pihilla in Walawwe paddy field | Sri Lanka Hada Bima Authority | Pallekotuwa | 175038.33 | Divisional Secretariat | 176748.93 | 175038.33 | 100% | 175038.33