## DCB MONTHLY PROGRESS
DISTRICT DECENTRALIZED PROJECT 2021 | [25 empty] | ඇමුණුම 01
Physical & Financial Progress on 2021.12.31
DS Division (a) |  | Name - Thumpane
No: 990
1 | Construction
අ.අ | Hon.Minister / MP | Project | Section | GN Division (b) |  | අංශය (c) (Sector) | Nature of the Project | Allocation |  | Total Estimation |  | Expenses | Messurement unit | Physical Progress (d ) | [9 empty] | Other |  | Number of beneficiaries | other | DS | PS | DS | PS
|  |  |  | Name | No |  |  | VAT | VAT Exluded |  |  |  |  | A | B |  |  |  | C | D | E | F | G
[15 empty] | B1 | B2 | B3 | B4
1 | Lohan Ratwatte | Ambagahahena Horagolla Road | RA | Ambagahahena | 371 |  | ඉදිකිරීම් |  | 200000 | 194174.75 |  | 194174.75 | [10 empty] | √ | අතති බිල් |  | 0 |  | √ |  | 200000
2 |  | Gallenawatta Water Well | WS | Gallenawatta | 364 |  | ඉදිකිරීම් |  | 100000 | 97087.3786 |  | 97087.38 | [10 empty] | √ | අතති බිල් |  | -0.0013592 |  | √ |  | 100000
3 |  | Medagoda Adikarampura 1st Lane | RA | Medagoda Ihala | 407 |  | ඉදිකිරීම් |  | 200000 | 194174.7573 | 192385.22 | 192385.22 | [10 empty] | √ |  |  | 1789.5373 |  |  | √ |  | 200000 | 5771.5566
4 | Lakshman Kiriella | Werellagama,Marawanagoda Sri Vajirarama Hall | RCS | Marawanagoda | 402 |  | ඉදිකිරීම් |  | 250000 | 242718.4466 |  | 242718.45 | [10 empty] | √ | අතති බිල් |  | -0.0033981 |  | √ |  | 250000
5 |  | Kumburegama, Sri Somananda Daham School Building | RCS | Kumburegama | 398 |  | ඉදිකිරීම් |  | 200000 | 194174.7573 | 194174.76 | 194174.76 | [10 empty] | √ |  |  | -0.0027184 |  | √ |  | 200000 |  | 5825.2427
6 | Ali Sabry | Drainage System Near by Mr.Razick's Residence | RA | Madige | 368 |  | ඉදිකිරීම් |  | 150000 | 145631.068 |  | 144944.96 | [10 empty] | √ | අතති බිල් |  | 686.108 |  | √ |  | 150000
7 | Rauf Hakeem | Kohila Ela Canal | MI | Madige South | 368 |  | ඉදිකිරීම් |  | 200000 | 194174.7573 |  | 194174.76 | [10 empty] | √ | අතති බිල් |  | -0.0027184 |  | √ |  | 200000
8 |  | Concrete Cricket Pitch for Jabbar Central College | ED | Madige | 368 |  | ඉදිකිරීම් |  | 50000 | 48543.6893 |  | 48543.69 | [10 empty] | √ | අතති බිල් |  | -0.00067961 |  | √ |  | 50000
9 | GL Pieris | Side Drainage system for Kuragama Settlement Road | RA | Kuragama | 365 |  | ඉදිකිරීම් |  | 245000 | 237864.0777 |  | 237864.08 | 1 | [9 empty] | √ | අතති බිල් |  | -0.0023301 |  | √ |  | 245000
10 |  | Monastry at Meegahahena Ashokaramaya | RCS | Meegahahena South | 380 |  | ඉදිකිරීම් |  | 145000 | 140776.699 | 140776.7 | 140776.7 | 2 | [9 empty] | √ |  |  | -0.00097087 |  | √ |  | 145000 |  | 4223.301
11 |  | Lavotary System at Monaragal Viharaya | RCS | Kaluwana | 318 |  | ඉදිකිරීම් |  | 245000 | 237864.0777 | 237864.08 | 237864.08 | 3 | [9 empty] | √ |  |  | -0.0023301 |  | √ |  | 245000 |  | 7135.9223
12 |  | Roofing the Bhikku Educational Institute at Medagoda Pirivena | RCS | Medagoda Pahala | 406 |  | ඉදිකිරීම් |  | 450000 | 436893.2039 |  | 436893.2 | 4 | [9 empty] | √ | අතති බිල් |  | 0.0038835 |  | √ |  | 450000
13 |  | Construction of side wall in front of the monastery of Henepola ancient temple | RCS | Tahalpitiya | 287 |  | ඉදිකිරීම් |  | 245000 | 237864.0777 |  | 231990.27 | 5 | [9 empty] | √ | අතති බිල් |  | 5873.8077 |  | √ |  | 245000
14 |  | Construction of Cloud Wall at Kannadeniya Gnanodaya Pirivena | RCS | Kannadeniya | 319 |  | ඉදිකිරීම් |  | 95000 | 92233.0097 |  | 92233.01 | 6 | [9 empty] | √ | අතති බිල් |  | -0.00029126 |  | √ |  | 95000
15 |  | Development of Galagedara Public Ground | PP | Udalagama | 309 |  | ඉදිකිරීම් |  | 375000 | 364077.6699 |  | 364077.67 | 7 | [9 empty] | √ | අතති බිල් |  | -9.7087e-05 |  |  | √ |  | 375000
16 |  | Development of the monastery building of the Gunadaha Rajamaha Viharaya | RCS | Gunadaha | 372 |  | ඉදිකිරීම් |  | 245000 | 237864.0777 | 237864.08 | 237864.08 | 8 | [9 empty] | √ |  |  | -0.0023301 |  | √ |  | 245000 |  | 7135.9224
17 |  | Development of Udalagama Division Pradeshiya Sabha Pre-School Building | ED | Udalagama | 309 |  | ඉදිකිරීම් |  | 195000 | 189150 |  | 179363.31 | 9 | [9 empty] | √ | අතති බිල් |  | 9786.69 |  |  | √ |  | 195000
18 |  | Development of Kadanhena Community Hall Building | RS | Kandanhena | 400 |  | ඉදිකිරීම් |  | 245000 | 237864.0777 |  | 232326.52 | 10 | [9 empty] | √ | අතති බිල් |  | 5537.5577 |  |  | √ |  | 245000
19 |  | Development of Ambagahahena Udakumbura Community Hall Building | RS | Ambagahahena | 371 |  | ඉදිකිරීම් |  | 145000 | 140776.699 |  | 140776.7 | 11 | [9 empty] | √ | අතති බිල් |  | -0.00097087 |  | √ |  | 145000
20 |  | Providing electricity for the Kiridiwelpola United Welfare Community Building and completing the rest of the development work | RS | Kirindiwelpola | 285 |  | ඉදිකිරීම් |  | 245000 | 237864.0777 |  | 237864.08 | 12 | [9 empty] | √ | අතති බිල් |  | -0.0023301 |  | √ |  | 245000
21 |  | Development activities of the United Welfare Center in Kuragama Colony | RS | Kuragama | 365 |  | ඉදිකිරීම් |  | 70000 | 67961.165 |  | 55403.44 | 13 | [9 empty] | √ | අතති බිල් |  | 12557.725 |  | √ |  | 70000
22 |  | Development of the road near Alawattegama temple | RA | Alawattegama | 399 |  | ඉදිකිරීම් |  | 245000 | 237864.0777 |  | 237864.08 | 14 | [9 empty] | √ | අතති බිල් |  | -0.0023301 |  | √ |  | 245000
23 | Dilum Amunugama | Development of Rock Hill Sri Bodhirukkarama Temple | RCS | Rock Hill | 302 |  | ඉදිකිරීම් |  | 75000 | 72815.534 |  | 72815.53 | [10 empty] | √ | අතති බිල් |  | 0.0039806 |  | √ |  | 75000
24 |  | Development of access road of Girihagama Sri Sumangalarama Temple | RA |  | 398 |  | ඉදිකිරීම් |  | 300000 | 291262.1359 |  | 291036.53 | [10 empty] | √ | අතති බිල් |  | 225.6059 |  | √ |  | 300000
25 |  | Development of Kobbegala Multipurpose Building | RS | Kobbegala | 370 |  | ඉදිකිරීම් |  | 50000 | 48543.6893 |  | 48543.69 | [10 empty] | √ | අතති බිල් |  | -0.00067961 |  | √ |  | 50000
26 | Gunathilaka Rajapaksha | Development of Multipurpose Building at Enamalpotha Senutthararama Temple | RS | Henegama Palkumbura | 405 |  | ඉදිකිරීම් |  | 100000 | 97087.3786 |  | 97087.38 | [10 empty] | √ | අතති බිල් |  | -0.0013592 |  | √ |  | 100000
|  | Total |  |  |  |  | 26 |  | 5065000 | 4917305.3325 | 1003064.84 | 4880848.32 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 26 |  | 3877783.48 | 36457.0125 |  | 22 | 4 | 4050000 | 1015000
2 | Purchassing
1 | Lakshman Kiriella | Chemical oil sprayer,aluminum 20 ft ladder and solar fencing for Banganga Rural Development Society | RS | BanAnga | 363 |  | මිලදී ගැනීම් |  | 100000 | 99000 |  | 99000 | [10 empty] | √ |  | 99000 | 0 |  | √ |  | 100000
2 | Mayantha Dissanayaka | Concrete mixing equipment (powered by electricity) for Banganga Rural Development Society | RS | BanAnga | 363 |  | මිලදී ගැනීම් |  | 200000 | 198000 |  | 198000 | [10 empty] | √ |  | 198000 | 0 |  | √ |  | 200000
3 |  | Purchase of Solar Light Pumps for Banganga Rural Development Society | RS | BanAnga | 363 |  | මිලදී ගැනීම් |  | 100000 | 99000 |  | 87000 | [10 empty] | √ |  | 87000 | 12000 |  | √ |  | 100000
4 | Udayana Kirindigoda | Buffet Set 01 for Retired War Heroes Forum of Henepola Poholiyadda | RS | Tahalpitiya | 286 |  | මිලදී ගැනීම් |  | 30000 | 29700 |  | 26987.04 | [10 empty] | √ |  | 26987.04 | 2712.96 |  | √ |  | 30000
5 |  | 30 nos of Non Stretch Plastic Chairs for Sandun Uyana Ekamuthu Welfare Society Kumburegama | RS | Andungama Palkumbura | 360 |  | මිලදී ගැනීම් |  | 30000 | 29700 |  | 29428.92 | [10 empty] | √ |  | 29428.92 | 271.08 |  | √ |  | 30000
6 |  | Buffet Set 01 for Henepola Thahalpitiya Samigi Welfare Society - Henepola Poholiyadda | RS | Tahalpitiya | 286 |  | මිලදී ගැනීම් |  | 30000 | 29700 |  | 26987.04 | [10 empty] | √ |  | 26987.04 | 2712.96 |  | √ |  | 30000
7 |  | Steel Cabinets 01 for Ekamuthu Elders Society - Naranwala, Hithgoda Walpola | RS | Hithgoda Walpola | 298 |  | මිලදී ගැනීම් |  | 15000 | 14850 |  | 13223.52 | [10 empty] | √ |  | 13223.52 | 1626.48 |  | √ |  | 15000
8 |  | Sports Equipment (Cricket Bat, Ball Ball, Volleyball Net)for Gunadaha Talent Sports Club, Gunadaha | RS | Gunadaha | 372 |  | මිලදී ගැනීම් |  | 20000 | 19800 |  | 19320 | [10 empty] | √ |  | 19320 | 480 |  | √ |  | 20000
9 |  | Buffet set - 02 for Sujatha United Funeral Aid Society Walpola, Wettewa. | RS | Hithgoda Walpola | 298 |  | මිලදී ගැනීම් |  | 30000 | 29700 |  | 26987.04 | [10 empty] | √ |  | 26987.04 | 2712.96 |  | √ |  | 30000
10 |  | 1000 liter water tank for Gunadaha Ekamuthu Welfare Society, Gunadaha. | RS | Gunadaha | 372 |  | මිලදී ගැනීම් |  | 15000 | 14850 |  | 12100 | [10 empty] | √ |  | 12100 | 2750 |  | √ |  | 15000
11 |  | Cooking Sauce Set 01 for Naranwala United Funeral Aid Society, Naranwala. | RS | Naranwala | 299 |  | මිලදී ගැනීම් |  | 20000 | 19800 |  | 19800 | [10 empty] | √ |  | 19800 | 0 |  | √ |  | 20000
12 | Velu Kumar | Donation of cricket equipment to Jabbar Central College (Leather) | ED | Madige | 368 |  | මිලදී ගැනීම් |  | 25000 | 24750 |  | 24750 | [10 empty] | √ |  | 24750 | 0 |  | √ |  | 25000
13 | Mahindananda Aluthgamage | Donation of plastic chairs for Paranagama Sudharma Women's Funeral Society | RS | Paranagama | 367 |  | මිලදී ගැනීම් |  | 20000 | 19800 |  | 19800 | [10 empty] | √ |  | 19800 | 0 |  | √ |  | 20000
14 |  | Donation of plastic chairs for Tennewela United Funeral Aid Society | RS | Thennewala | 292 |  | මිලදී ගැනීම් |  | 20000 | 19800 |  | 19800 | [10 empty] | √ |  | 19800 | 0 |  | √ |  | 20000
15 |  | Donation of plastic chairs for the United Funeral Aid Society, Naranwala | RS | Naranwala | 299 |  | මිලදී ගැනීම් |  | 20000 | 19800 |  | 19800 | [10 empty] | √ |  | 19800 | 0 |  | √ |  | 20000
16 |  | Donation of plastic chairs for Uduwa Pottila Funeral Society | RS | Pottila | 313 |  | මිලදී ගැනීම් |  | 20000 | 19800 |  | 19800 | [10 empty] | √ |  | 19800 | 0 |  | √ |  | 20000
17 |  | Donation of plastic chairs for Idamegama Niyambepola United Welfare Funeral Society | RS | Idamegama | 404 |  | මිලදී ගැනීම් |  | 20000 | 19800 |  | 19800 | [10 empty] | √ |  | 19800 | 0 |  | √ |  | 20000
18 |  | Donation of plastic chairs for Marawanagoda Dimbulkumbura United Welfare Society | RS | Marawanagoda | 402 |  | මිලදී ගැනීම් |  | 20000 | 19800 |  | 19800 | [10 empty] | √ |  | 19800 | 0 |  | √ |  | 20000
19 | Anuradha Jayarathna | Donation of chairs to Udukumbura United Funeral Aid Society | RS | Ambagahahena | 371 |  | මිලදී ගැනීම් |  | 30000 | 29700 |  | 29700 | [10 empty] | √ |  | 29700 | 0 |  | √ |  | 30000
20 | Prof Ranjith Bandara | Providing materials for the construction of the building of the ancient Sri Bodhirukkarama Temple | RCS | Medagoda Pahala | 406 |  | මිලදී ගැනීම් |  | 200000 | 198000 |  | 197730 | [10 empty] | √ |  | 197730 | 270 |  | √ |  | 200000
21 | GL Pieris | Donation of chairs to Niyangoda North Welfare Society | RS | Niyangoda | 358 |  | මිලදී ගැනීම් |  | 20000 | 19800 |  | 19800 | 1 | [9 empty] | √ |  | 19800 | 0 |  | √ |  | 20000
22 |  | Donation of chairs to Diyapalagoda Funeral and Welfare Society | RS | Diyapalagoda | 359 |  | මිලදී ගැනීම් |  | 20000 | 19800 |  | 19800 | 2 | [9 empty] | √ |  | 19800 | 0 |  | √ |  | 20000
23 |  | Donating a buffet set to the Ethamulla Funeral and Development Welfare Society | RS | Ethamulla | 362 |  | මිලදී ගැනීම් |  | 20000 | 19800 |  | 19258.56 | 3 | [9 empty] | √ |  | 19258.56 | 541.44 |  | √ |  | 20000
24 |  | Donation of chairs to Girihagama Funeral Society | RS | Kumburegama | 398 |  | මිලදී ගැනීම් |  | 45000 | 44550 |  | 44550 | 4 | [9 empty] | √ |  | 44550 | 0 |  | √ |  | 45000
25 |  | Donating a Canopy Hut to the United Welfare and Funeral Aid Society | RS | Kumburegama | 398 |  | මිලදී ගැනීම් |  | 20000 | 19800 |  | 19800 | 5 | [9 empty] | √ |  | 19800 | 0 |  | √ |  | 20000
26 |  | Providing a buffet set to the Women's Welfare Society | RS | Alawattegama | 399 |  | මිලදී ගැනීම් |  | 20000 | 19800 |  | 19258.56 | 6 | [9 empty] | √ |  | 19258.56 | 541.44 |  | √ |  | 20000
27 |  | Donation of chairs to Yashoda Women's Society | RS | Kumburegama | 398 |  | මිලදී ගැනීම් |  | 20000 | 19800 |  | 19800 | 7 | [9 empty] | √ |  | 19800 | 0 |  | √ |  | 20000
28 |  | Providing a buffet set for Atambegoda Welfare and Funeral Society | RS | Dehideniya | 284 |  | මිලදී ගැනීම් |  | 20000 | 19800 |  | 19258.56 | 8 | [9 empty] | √ |  | 19258.56 | 541.44 |  | √ |  | 20000
29 |  | Donating a buffet set to Hapugahaela Udawatte United Welfare and Funeral Society | RS | Udahenepola | 287 |  | මිලදී ගැනීම් |  | 20000 | 19800 |  | 19258.56 | 9 | [9 empty] | √ |  | 19258.56 | 541.44 |  | √ |  | 20000
30 |  | Donating a Buffet Set to Giranthalawa United Welfare Society | RS | Etambegoda | 290 |  | මිලදී ගැනීම් |  | 20000 | 19800 |  | 19800 | 10 | [9 empty] | √ |  | 19800 | 0 |  | √ |  | 20000
31 |  | Donating a buffet set to Thahalpitiya Medagama United Funeral Aid Welfare Society | RS | Tahalpitiya | 286 |  | මිලදී ගැනීම් |  | 20000 | 19800 |  | 17699.04 | 11 | [9 empty] | √ |  | 17699.04 | 2100.96 |  | √ |  | 20000
32 |  | Providing chairs for Poholiyadda United Funeral Aid Society | RS | Poholiyadda | 288 |  | මිලදී ගැනීම් |  | 35000 | 34650 |  | 34650 | 12 | [9 empty] | √ |  | 34650 | 0 |  | √ |  | 35000
33 |  | Providing a saucepan set for Poholiyadda Visakha Women's Society | RS | Poholiyadda | 288 |  | මිලදී ගැනීම් |  | 5000 | 4950 |  | 3069.36 | 13 | [9 empty] | √ |  | 3069.36 | 1880.64 |  | √ |  | 5000
34 |  | Purchase of materials required for the construction of the front fence of Medagama Vidyalaya | RS | Poholiyadda | 288 |  | මිලදී ගැනීම් |  | 95000 | 94050 |  | 94050 | 14 | [9 empty] | √ |  | 94050 | 0 |  | √ |  | 95000
35 |  | Purchase of a buffet set for Gothami Women's Society | RS | Barandara | 322 |  | මිලදී ගැනීම් |  | 35000 | 34650 |  | 34650 | 15 | [9 empty] | √ |  | 34650 | 0 |  | √ |  | 35000
36 |  | Purchase of a Multimedia Projector for Asoka Primary School, Meegahahena | RS | Meegahahena South | 380 |  | මිලදී ගැනීම් |  | 65000 | 64350 |  | 64350 | 16 | [9 empty] | √ |  | 64350 | 0 |  | √ |  | 65000
37 |  | Purchase of a saucepan set for the Pubbiliya Visakha Women's Society | RS | Pubbiliya | 321 |  | මිලදී ගැනීම් |  | 15000 | 14850 |  | 14850 | 17 | [9 empty] | √ |  | 14850 | 0 |  | √ |  | 15000
38 |  | Purchase of Plastic Chairs for Kobbegala, Pahalagama, Udagama Joint Funeral Aid Society | RS | Kobbegala | 370 |  | මිලදී ගැනීම් |  | 15000 | 14850 |  | 14726.88 | 18 | [9 empty] | √ |  | 14726.88 | 123.12 |  | √ |  | 15000
39 |  | Purchase of plastic chairs for Visakha Women's Society, Kahapathwala, Bettiyagoda; | RS | Meegahahena South | 380 |  | මිලදී ගැනීම් |  | 10000 | 9900 |  | 9900 | 19 | [9 empty] | √ |  | 9900 | 0 |  | √ |  | 10000
40 |  | Purchase of chairs for Galabawa, Gangodapitiya United Funeral Society | RS | Galabawa | 378 |  | මිලදී ගැනීම් |  | 15000 | 14850 |  | 14850 | 20 | [9 empty] | √ |  | 14850 | 0 |  | √ |  | 15000
41 |  | Purchase of a Canopy Hut for Meegahahena Sahana Shakthi Mithuru Hawula Welfare Society | RS | Meegahahena North | 379 |  | මිලදී ගැනීම් |  | 30000 | 29700 |  | 29700 | 21 | [9 empty] | √ |  | 29700 | 0 |  | √ |  | 30000
42 |  | Purchase of roofing sheets for Madawala Charitable Society, Kopiwatta | RS | Palukopiwatta | 308 |  | මිලදී ගැනීම් |  | 45000 | 44550 |  | 43750 | 22 | [9 empty] | √ |  | 43750 | 800 |  | √ |  | 45000
43 |  | Purchase of a Canopy Hut for Banganga East United Funeral and Welfare Society | RS | BanAnga | 363 |  | මිලදී ගැනීම් |  | 45000 | 44550 |  | 44550 | 23 | [9 empty] | √ |  | 44550 | 0 |  | √ |  | 45000
44 |  | Donating a buffet set to the South United Funeral Aid Society | RS | Marawanagoda | 402 |  | මිලදී ගැනීම් |  | 45000 | 44550 |  | 44247.6 | 24 | [9 empty] | √ |  | 44247.6 | 302.4 |  | √ |  | 45000
45 |  | Providing a glassless cupboard and office desks to the North Samagi Funeral Aid Society | RS | Marawanagoda | 402 |  | මිලදී ගැනීම් |  | 45000 | 44550 |  | 37780.56 | 25 | [9 empty] | √ |  | 37780.56 | 6769.44 |  | √ |  | 45000
46 |  | Donation of plastic chairs to Enamalpotha Thibbutta United Funeral Aid and Welfare Society | RS | Henegama Palkumbura | 405 |  | මිලදී ගැනීම් |  | 45000 | 44550 |  | 44550 | 26 | [9 empty] | √ |  | 44550 | 0 |  | √ |  | 45000
47 |  | Purchase of chairs for Ambagahahena United Funeral Aid Society | RS | Ambagahahena | 371 |  | මිලදී ගැනීම් |  | 45000 | 44550 |  | 44550 | 27 | [9 empty] | √ |  | 44550 | 0 |  | √ |  | 45000
48 |  | Purchase of chairs for Opalla United Funeral Aid Society | RS | Opalla | 373 |  | මිලදී ගැනීම් |  | 45000 | 44550 |  | 44550 | 28 | [9 empty] | √ |  | 44550 | 0 |  | √ |  | 45000
49 |  | Purchase of a Generator for Yasa Isuru Welfare Society, Court Road | RS | Galagedara West | 301 |  | මිලදී ගැනීම් |  | 45000 | 44550 |  | 44550 | 29 | [9 empty] | √ |  | 44550 | 0 |  | √ |  | 45000
50 |  | Purchase of a Canopy Hut for United Welfare and Funeral Assistance | RS | Udapitiya | 311 |  | මිලදී ගැනීම් |  | 45000 | 44550 |  | 44550 | 30 | [9 empty] | √ |  | 44550 | 0 |  | √ |  | 45000
51 |  | Obtaining a Steel Cabinets for the Abinawa Praboda Welfare Society | RS | Galagedara West | 301 |  | මිලදී ගැනීම් |  | 20000 | 19800 |  | 19800 | 31 | [9 empty] | √ |  | 19800 | 0 |  | √ |  | 20000
52 |  | Purchase of a Canopy Hut for the Maanasa Welfare Society | RS | Galagedara West | 301 |  | මිලදී ගැනීම් |  | 45000 | 44550 |  | 44550 | 32 | [9 empty] | √ |  | 44550 | 0 |  | √ |  | 45000
53 |  | Purchase of chairs for Naranwala United Funeral Aid Society | RS | Naranwala | 299 |  | මිලදී ගැනීම් |  | 45000 | 44550 |  | 44550 | 33 | [9 empty] | √ |  | 44550 | 0 |  | √ |  | 45000
54 |  | Purchase of chairs for Hitgoda Walpola Sujatha United Funeral Aid Society | RS | Hithgoda Walpola | 298 |  | මිලදී ගැනීම් |  | 45000 | 44550 |  | 44550 | 34 | [9 empty] | √ |  | 44550 | 0 |  | √ |  | 45000
55 |  | Purchase of a file cupboard,Amano sheets for Ekamuthu Funeral Society | RS | Rock Hill | 302 |  | මිලදී ගැනීම් |  | 35000 | 34650 |  | 34650 | 35 | [9 empty] | √ |  | 34650 | 0 |  | √ |  | 35000
56 |  | Purchase of plastic chairs for Rockhill Akkarawatta United Funeral Aid Society | RS | Rock Hill | 302 |  | මිලදී ගැනීම් |  | 35000 | 34650 |  | 34650 | 36 | [9 empty] | √ |  | 34650 | 0 |  | √ |  | 35000
57 |  | Purchase of plastic chairs for Delgasyaya United Welfare Funeral Society | RS | Delgasyaya | 307 |  | මිලදී ගැනීම් |  | 35000 | 34650 |  | 34650 | 37 | [9 empty] | √ |  | 34650 | 0 |  | √ |  | 35000
58 |  | Purchase of a generator for Malpolayaya United Funeral Aid Society | RS | Udalagama | 309 |  | මිලදී ගැනීම් |  | 35000 | 34650 |  | 34650 | 38 | [9 empty] | √ |  | 34650 | 0 |  | √ |  | 35000
59 |  | Purchase of a Canopy Hut for the United Welfare Society | RS | Kaluwana | 318 |  | මිලදී ගැනීම් |  | 45000 | 44550 |  | 44550 | 39 | [9 empty] | √ |  | 44550 | 0 |  | √ |  | 45000
60 |  | Purchase of a canopy hut for Medagoda Pahala Youth Union Welfare Society | RS | Medagoda Pahala | 406 |  | මිලදී ගැනීම් |  | 45000 | 44550 |  | 44550 | 40 | [9 empty] | √ |  | 44550 | 0 |  | √ |  | 45000
61 |  | Providing roofing sheets to the Funeral and Welfare Society | RS | Alawattegama |  |  | මිලදී ගැනීම් |  | 20000 | 19800 |  | 18750 | 41 | [9 empty] | √ |  | 18750 | 1050 |  | √ |  | 20000
62 |  | Purchase of a Canopy Hut for the United Welfare Funeral Aid Society | RS | Gallenawatta |  |  | මිලදී ගැනීම් |  | 45000 | 44550 |  | 44550 | 42 | [9 empty] | √ |  | 44550 | 0 |  | √ |  | 45000
63 |  | Purchase of a Canopy Hut for the Wettewa United Funeral Aid Society | RS | Wettewa |  |  | මිලදී ගැනීම් |  | 45000 | 44550 |  | 44550 | 43 | [9 empty] | √ |  | 44550 | 0 |  | √ |  | 45000
64 |  | Purchase of a Canopy Hut for the Uda Aramba United Funeral Aid Society,Pethigewela | RS | Pethigewala |  |  | මිලදී ගැනීම් |  | 35000 | 34650 |  | 34650 | 44 | [9 empty] | √ |  | 34650 | 0 |  | √ |  | 35000
65 |  | Purchase of a canopy hut for the Palukopiwatta United Funeral Aid Society. | RS | Palukopiwatta |  |  | මිලදී ගැනීම් |  | 45000 | 44550 |  | 44550 | 45 | [9 empty] | √ |  | 44550 | 0 |  | √ |  | 45000
66 |  | Donating a buffet set to Kandekumbura United Philanthropic Society | RS | Kandekumbura |  |  | මිලදී ගැනීම් |  | 20000 | 19800 |  | 19800 | 46 | [9 empty] | √ |  | 19800 | 0 |  | √ |  | 20000
67 |  | Purchase of an amp, buffel set and a microphone for the Henepola Thahalpitiya Samagi Welfare Society | RS | Tahalpitiya | 286 |  | මිලදී ගැනීම් |  | 20000 | 19800 |  | 19800 | 47 | [9 empty] | √ |  | 19800 | 0 |  | √ |  | 20000
68 |  | Donating a buffet set to Pallekotuwa Funeral Aid and United Welfare Society | RS | Pallekotuwa | 392 |  | මිලදී ගැනීම් |  | 20000 | 19800 |  | 17699.04 | 48 | [9 empty] | √ |  | 17699.04 | 2100.96 |  | √ |  | 20000
69 |  | Donation of a saucepan set to Nikathenna Ubhaya Lokartha Funeral Aid Society | RS | Nikathenna | 289 |  | මිලදී ගැනීම් |  | 20000 | 19800 |  | 19800 | 49 | [9 empty] | √ |  | 19800 | 0 |  | √ |  | 20000
70 |  | Donation of plastic chairs to Dimbulkumbura United Welfare Society | RS | Niyambepola | 403 |  | මිලදී ගැනීම් |  | 45000 | 44550 |  | 44550 | 50 | [9 empty] | √ |  | 44550 | 0 |  | √ |  | 45000
71 |  | Donation of plastic chairs to Idamegama Ekamuthu Community Center | RS | Idamegama | 404 |  | මිලදී ගැනීම් |  | 45000 | 44550 |  | 44550 | 51 | [9 empty] | √ |  | 44550 | 0 |  | √ |  | 45000
72 |  | Donation of plastic chairs to Adungama Palkumbura Ekamuthu Rural Development Society | RS | Andungama Palkumbura | 360 |  | මිලදී ගැනීම් |  | 45000 | 44550 |  | 44550 | 52 | [9 empty] | √ |  | 44550 | 0 |  | √ |  | 45000
73 |  | Purchase of amano sheets, a set of saucepans and a buffet set for Visakha United Funeral Society, Damunugastenna | RS | Damunugasthenna | 306 |  | මිලදී ගැනීම් |  | 45000 | 44550 |  | 43750 | 53 | [9 empty] | √ |  | 43750 | 800 |  | √ |  | 45000
74 |  | purchasing Chairs for the Sri Parakrama United Funeral Aid Society, Medagoda | RS | Medagoda Ihala | 407 |  | මිලදී ගැනීම් |  | 35000 | 34650 |  | 34650 | 54 | [9 empty] | √ |  | 34650 | 0 |  | √ |  | 35000
75 |  | Purchasing materials for setting up the children's park at Wettewa Primary School (GI pipes, chains, wires, etc.) | ED | Wettewa | 296 |  | මිලදී ගැනීම් |  | 70000 | 69300 |  | 69216 | 55 | [9 empty] | √ |  | 69216 | 84 |  | √ |  | 70000
76 |  | Purchase of plastic chairs for Kannadeniya United Funeral Aid Society | RS | Kannadeniya | 319 |  | මිලදී ගැනීම් |  | 25000 | 24750 |  | 24750 | 56 | [9 empty] | √ |  | 24750 | 0 |  | √ |  | 25000
77 |  | Purchase of a Canopy Hut for the United Welfare Society | RS | Namalthenna | 401 |  | මිලදී ගැනීම් |  | 45000 | 44550 |  | 44550 | 57 | [9 empty] | √ |  | 44550 | 0 |  | √ |  | 45000
78 |  | Purchase of roofing sheets for Uduwa Kanda United Funeral Society | RS | Pottila | 372 |  | මිලදී ගැනීම් |  | 35000 | 34650 |  | 34650 | 58 | [9 empty] | √ |  | 34650 | 0 |  | √ |  | 35000
79 |  | Purchase of roofing sheets and pipes for Kalugalawatta Samagi Welfare and Funeral Society; | RS | Gunadaha | 372 |  | මිලදී ගැනීම් |  | 90000 | 89100 |  | 83440 | 59 | [9 empty] | √ |  | 83440 | 5660 |  | √ |  | 90000
91 |  | Providing chairs for Atambegoda Dehideniya Buddhist Association | RS | Etambegoda |  |  | මිලදී ගැනීම් |  | 20000 | 19800 |  | 19800 | 60 | [9 empty] | √ |  | 19800 | 0 |  | √ |  | 20000
92 |  | Purchasing a Canopy Hut for Rockhill Funeral Society | RS | Rock Hill |  |  | මිලදී ගැනීම් |  | 100000 | 99000 |  | 99000 | 61 | [9 empty] | √ |  | 99000 | 0 |  | √ |  | 100000
93 |  | Purchase of a Canopy Hut for the Galagedara United Trade Union | RS | Galagedara West |  |  | මිලදී ගැනීම් |  | 100000 | 99000 |  | 99000 | 62 | [9 empty] | √ |  | 99000 | 0 |  | √ |  | 100000
94 |  | Obtaining Plastic Chairs for Galagedara MANASA Welfare Society | RS | Galagedara West |  |  | මිලදී ගැනීම් |  | 45000 | 44550 |  | 44550 | 63 | [9 empty] | √ |  | 44550 | 0 |  | √ |  | 45000
80 | M.H.A Haleem | Donation of plastic chairs to Sri Vajirarama Temple, Marawanagoda, Werellagama. | RS | Marawanagoda |  |  | මිලදී ගැනීම් |  | 30000 | 29700 |  | 29700 | [10 empty] | √ |  | 29700 | 0 |  | √ |  | 30000
81 | Dilum Amunugama | Purchasing a Buffet Set for Sawbagya Women Agriculture Project Organization | RS | Pottila |  |  | මිලදී ගැනීම් |  | 20000 | 19800 |  | 17699.04 | [10 empty] | √ |  | 17699.04 | 2100.96 |  | √ |  | 20000
82 |  | Purchasing a Buffet Set for Kadanhena Achini Women's Society | RS | Kandanhena |  |  | මිලදී ගැනීම් |  | 20000 | 19800 |  | 17699.04 | [10 empty] | √ |  | 17699.04 | 2100.96 |  | √ |  | 20000
83 |  | Purchasing a Buffet Set for the Henegama Palkumbura Visakha Women's Society | RS | Henegama Palkumbura |  |  | මිලදී ගැනීම් |  | 20000 | 19800 |  | 19800 | [10 empty] | √ |  | 19800 | 0 |  | √ |  | 20000
84 |  | Obtaining cushioned chairs for the Welfare Society of Thumpane Divisional Secretariat | RS | Haddapitiya |  |  | මිලදී ගැනීම් |  | 20000 | 19800 |  | 19800 | [10 empty] | √ |  | 19800 | 0 |  | √ |  | 20000
85 |  | Obtaining 20 Chairs for Udubogawa Siri Sidhuhath Dhamma School (Sri Wijewardanaramaya) | RCS | Paranagama |  |  | මිලදී ගැනීම් |  | 20000 | 19800 |  | 19800 | [10 empty] | √ |  | 19800 | 0 |  | √ |  | 20000
86 |  | Obtaining Sporting Goods (Leather Balls) for Jabar Maha Vidyalaya, Galagedara | ED | Madige |  |  | මිලදී ගැනීම් |  | 50000 | 49500 |  | 49500 | [10 empty] | √ |  | 49500 | 0 |  | √ |  | 50000
87 |  | Providing 20 Plastic chairs for Bogahalanda Aid Society | RS | Galagedara |  |  | මිලදී ගැනීම් |  | 15000 | 14850 |  | 14726.88 | [10 empty] | √ |  | 14726.88 | 123.12 |  | √ |  | 15000
88 |  | Providing 20 Plastic chairs for Shakthi Funeral Aid Society | RS | Rock Hill |  |  | මිලදී ගැනීම් |  | 15000 | 14850 |  | 14850 | [10 empty] | √ |  | 14850 | 0 |  | √ |  | 15000
89 |  | Purchasing 20 Plastic Chairs for Paranagama Sudharma Women's Funeral Aid Society | RS | Paranagama |  |  | මිලදී ගැනීම් |  | 15000 | 14850 |  | 14726.88 | [10 empty] | √ |  | 14726.88 | 123.12 |  | √ |  | 15000
90 | Gunathilaka Rajapaksha | Providing plastic chairs for Marawanagoda North Rural Development Society | RS | Marawanagoda |  |  | මිලදී ගැනීම් |  | 25000 | 24750 |  | 24682.32 | [10 empty] | √ |  | 24682.32 | 67.68 |  | √ |  | 25000
[7 empty] | 94 |  | 3585000 | 3549150 |  | 3495260.44 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 94 |  |  | 12 |  | 94 | 0 | 3585000 | 0
[7 empty] | 120 |  | 8650000 | 8466455.3325 |  | 8376108.76 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 120 |  |  | 36469.0125 |  | 116 | 4 | 7635000 | 1015000 | 8650000